## Overview & responsibilities
University of South-Eastern Norway (USN)
HRS4R Action Plan 2022-2025 (Charter & Code)
Proposed action | Deadline | Responsible Unit | Responsible for implementation / reporting | Involved / Contributors | Status | Comments
ETHICAL and PROFESSIONAL ASPECTS
Revise language policy | 4Q_22 | Dept. of Personnel and Organisation | Borhaug | Brørs (PO) / Tvedt (AFI) / Glückstad Karlsen (AUS) / Larsen (KOM) | In progress | Incl. language courses and all info avaiable in both Norwegian and English
Implement new templates for annual appraisal meeting | 4Q_22 | Dept. of Personnel and Organisation | Parelius | Brørs (PO) / IORL | In progress | Pilot completed. Ready for implementation.
RECRUITMENT and SELECTION
Further develop and strengthen strategic recruitment of researchers | 1Q_23 | Dept. of Personnel and Organisation | Borhaug | Granseth Wien (PO) / Slagsvold / Ormstad (AFI) | In progress | Clarifying research group affiliation in revised templates for job announcements. Increase involvment of research groups in recruitment processes through participation in interviewpanels. Stimulating the use of post. doc. positions in the template for recruitment planning.
Adaptation and implementation of the NOR_CAM criteria for employment and promotion | 2Q_23 | Dept. of Personnel and Organisation | Granseth Wien | Slagsvold / Ormstad / Strøm (AFI) Sommerset / Hyllseth Matsen (PO) |  | Seen in connectinon with similar processes at European level (YERUN / EDUC)
WORKING CONDITIONS and SOCIAL SECURITY
Strengthened on-boarding | 2Q_23 | Dept. of Personnel and Organisation | Granseth Wien | Slagsvold / Ormstad / Enstad (AFI) | In progress | Especially for PhDs / foreign background. Incl. practical, sosial and prof. start-up conversations, webinars / campus gatherings
Develop and implement research policy | 4Q_22 | Dept. of Research and Internationalisation | Slagsvold | Ormstad / Faculties | In progress | Establishing the framework for research groups / research centers / research managers / etc.
Develop and implement career policy | 2Q_24 | Dept. of Personnel and Organisation | Borhaug | Slagsvold / Ormstad (AFI) / Fak. |  | Adressing mentoring, mobility x 3, sabbatical leave, dual careers, post. doc.positions etc. Seen in connection with USN Research Policy.
Establish career guidance services | 2Q_24 | Dept. of Personnel and Organisation | Borhaug | Slagsvold / Ormstad (AFI) |  | Consultations, courses, webinars, gatherings, websites.
Implement new templates for individual career develoment plan | 1Q_23 | Dept. of Personnel and Organisation | Parelius | Brørs (PO) / IORL | In progress | Pilot completed. Ready for implementation.
Establish institutional uniform practice for financing of research mobility | 4Q_22 | Dept. of Research and Internationalisation | Slagsvold | Faculties |  | AFI to initiate dialogue with Faculties on how to establish more sytematic arrangements for financing of mobility within the contstraint of existing budgets
Further develop and strengthen 'USN Staff Mobility Team' | 4Q_22 | Dept. of Personnel and Organisation | Borhaug | Slagsvold (AFI) / Thomassen (ØKO) | In progress | Provided given priority / funding. Pending clarification with Rector / University Director
Develop overview of strategic partner institutions relevant PhD/staff mobility , as well as manual for how to proceed | 4Q_22 | Dept. of Research and Internationalisation | Tovsrud Knutsen
Facilitate start-up of PhD union at USN and enrollment in the national PhD association | 4Q_22 | Dept. of Research and Internationalisation | Slagsvold | Faculties / Enstad (AFI) / Brørs (PO) | In progress
Establish annual institutional PhD gathering for all PhD candidates | 4Q_22 | Dept. of Research and Internationalisation | Slagsvold | Faculties / Enstad (AFI) / Brørs (PO) | In progress | Focusing on ex. mobility, career develoment, psycosocial working environment and establishing of USN PhD Union.
Allow for PhD candidates to attend cources in UH-ped | 3Q_22 | Dept. of Personnel and Organisation | Borhaug | Marheim Larsen (Rectorate) / Bredahl (Dept. of Education and Quality in Learning)
Establish practice for discussing workning environment surveys concerning Phd candidates in the Workning Environment Committee (HAMU) | 3Q_22 | Dept. of Personnel and Organisation | Borhaug | Reitan (PO)
TRAINING and DEVELOPMENT
Develop and implement research management traning program | 4Q_23 | Dept. of Personnel and Organisation | Borhaug | Slagsvold (AFI) |  | Incl. leadership training in diversity management
Further develop and implement development programs for research talent | 4Q_22 | Dept. of Research and Internationalisation | Slagsvold |  | In progress | MSCA / ERC candidates
Develop and implement e -learning / webinars for newly recruited researchers | 2Q_23 | Dept. of Personnel and Organisation | Parelius | Brørs / Rykkje Lindgård (PO) Beckman / Strøm (AFI) |  | Incl. ethics, IPR, OA, rules and regulations, publication etc.
Develop and implement introductory course in Norwegian culture and working life | 4Q_22 | Dept. of Personnel and Organisation | Granseth Wien |  |  | As part of strengthening of on-boarding.