## Plan of progress
Plan of progress - implementation of the Action plan 2022 - 2025
|  | Dept. of Personnel and Organisation | [18 empty] | Dept. of Personnel and Organisation | [11 empty] | Dept. of Personnel and Organisation | [11 empty] | Dept. of Personnel and Organisation
|  | Dept. of Research and Internationalisation | [18 empty] | Dept. of Research and Internationalisation | [11 empty] | Dept. of Research and Internationalisation | [11 empty] | Dept. of Research and Internationalisation
|  | Dept. of Communication | [18 empty] | Dept. of Communication | [11 empty] | Dept. of Communication | [11 empty] | Dept. of Communication
|  | Dept. of Infrastructure | [18 empty] | Dept. of Infrastructure | [11 empty] | Dept. of Infrastructure | [11 empty] | Dept. of Infrastructure
| Actions to be implemented (and status) / time span | 2 0 22 | [11 empty] | 2 0 23 | [11 empty] | 2 0 24 | [11 empty] | 2 0 25
|  | JAN | FEB | MARS | APRIL | MAY | JUNE | JULY | AUGUST | SEPT | OCT | NOV | DEC | JAN | FEB | MARS | APRIL | MAY | JUNE | JULY | AUGUST | SEPT | OCT | NOV | DEC | JAN | FEB | MARS | APRIL | MAY | JUNE | JULY | AUGUST | SEPT | OCT | NOV | DEC | JAN | FEB | MARS | APRIL | MAY | JUNE | JULY | AUGUST | SEPT | OCT | NOV | DEC
ETHICAL and PROFESSIONAL ASPECTS
Revise language policy | bar: 2 0 22 MAY to 2 0 22 JUNE
Implement new templates for annual appraisal meeting | bar: 2 0 22 MAY to 2 0 22 JUNE
RECRUITMENT and SELECTION
Further develop and strengthen strategic recruitment of researchers | bar: 2 0 22 AUGUST to 2 0 23 MARS
NEW | Adaptation and implementation of the NOR_CAM criteria for employment and promotion | bar: 2 0 22 OCT to 2 0 23 JUNE
WORKING CONDITIONS and SOCIAL SECURITY
NEW | Strengthened on-boarding | bar: 2 0 22 SEPT to 2 0 23 JUNE
Develop and implement research policy | bar: 2 0 22 MAY to 2 0 22 JUNE
Develop and implement career policy | bar: 2 0 23 JAN to 2 0 23 JUNE; 2 0 23 AUGUST to 2 0 24 JUNE
Establish career guidance services | bar: 2 0 22 NOV to 2 0 23 JUNE; 2 0 23 AUGUST to 2 0 24 JUNE
Implement new templates for individual career develoment plan | bar: 2 0 22 MAY to 2 0 22 JUNE; 2 0 22 AUGUST to 2 0 23 MARS
Establish institutional uniform practice for financing of research mobility | bar: 2 0 22 MAY to 2 0 22 JUNE
Further develop and strengthen 'USN Staff Mobility Team'
NEW | Develop overview of strategic partner institutions relevant PhD/staff mobility , as well as manual for how to proceed
NEW | Facilitate start-up of PhD union at USN and enrollment in the national PhD association | bar: 2 0 22 MAY to 2 0 22 JUNE
NEW | Establish annual institutional PhD gathering for all PhD candidates | bar: 2 0 22 MAY to 2 0 22 JUNE
NEW | Allow for PhD candidates to attend cources in UH-ped | bar: 2 0 22 AUGUST to 2 0 22 SEPT
NEW | Establish practice for discussing workning environment surveys concerning Phd candidates in the Workning Environment Committee (HAMU) | bar: 2 0 22 AUGUST to 2 0 22 SEPT
TRAINING and DEVELOPMENT
Develop and implement research management traning program | bar: 2 0 23 JAN to 2 0 23 JUNE; 2 0 23 AUGUST to 2 0 23 DEC
Further develop and implement development programs for research talent | bar: 2 0 22 MAY to 2 0 22 JUNE
Develop and implement e -learning / webinars for newly recruited researchers | bar: 2 0 22 AUGUST to 2 0 23 JUNE
NEW | Develop and implement introductory course in Norwegian culture and working life | bar: 2 0 22 JUNE
Main responsibility - Department of Personnel and organisation
Main responsibility - Department of Research and Internationalisation