## Overview & responsibilities
University of South-Eastern Norway (USN)
Completed
On-going
| HRS4R Action Plan 2025-2028 - Implementing the European Charter for Researchers |  |  |  |  | On- hold / delayed / changed
No. | Proposed action | Further specification | Status | Related to principle | Deadline | Responsible Department | Responsible Unit | Responsible for implementation / reporting | Involved / Contributors | Status | Comments
PILLAR 1: Ethics, Integrity, Gender and Open Science
1 | Organisational development project aimed at ensuring compliance with research ethics standards. | Review existing arrangements and identifying areas of improvement in order to ensure that the institution has a research culture that promotes responsible and ethical research, which includes strengthening on-boarding and training for newly recruited researchers. | on-going | Pillar 1, principle 1 Pillar 4, principle 3 | 4Q_2025 | Dept. of Research, Innovation and Library |  | Magnus Egan (Senior Advisor) |  |  | A status report on research ethics at USN was presented to the Research and Innovation Committee on 26 September 2025. The Committee reviewed ongoing initiatives and endorsed a number of priority actions aimed at strengthening the institutional framework for research integrity. These included the implementation of mandatory research ethics training for staff and the establishment of a local research ethics committee.
PILLAR 2: Researchers’ Assessment, Recruitment and Progression
2 | Develop and implement USN-Career Assessment Matrix. | In accordance with national (NOR-CAM) and European (CoARA) reform of qualifications criteria for academic employment and promotion. | on-going | Pillar 2, principle 1 Pillar 1, principle 7 | 4Q_2025 | Dept. of Personnel and Organisation | Recruitment Unit | Head of Recruitment Unit | Dept. of Research, Innovation and Library: - Research and Research Education Unit - University Library - Vice rector |  | Developed and implemented
3 | Further implement use of EURAXESS portal. | Ensure that all open positions (unless explicitly not relevant) are advertised on the EURAXESS portal, and that level and type of position, as well as valuation of mobility experience and career opportunities, are clearly described. | on-going | Pillar 2, principle 2 | 2Q_2026 | Dept. of Personnel and Organisation | Recruitment Unit | Head of Recruitment Unit | Heads of Department at Faculties |  | Practice in place, most relevant announcements at EURAXESS. Automatic solution for postng open positions to be explored.
4 | Revise and implement new guidelines for recruitment of PhD and Post Doc positions. | This guidelines is an integration of new national legislation at USN, strengthening the framework for early stage research careers (R1-R2) | on-going | Pillar 2, principle 2 | 4Q_2025 | Dept. of Personnel and Organisation | Recruitment Unit | Head of Recruitment Unit | Heads of Department at Faculties |  | Guidelines are in place.
PILLAR 3: Working Conditions and Practices
5 | Organisational development project aimed at strengthening psychosocial working conditions for international PhDs. | The mandate for this project is to: - ensure adequate access to psychosocial support - identifying and implementing best practice for psychosocial well-being (i.e. "buddy system", cross faculty/program social activities, access to courses in stress management / work life balance etc.) | on-going | Pillar 1, principle 1 | 4Q_2025 | Dept. of Research, Innovation and Library |  | Mette Lene Falck Pedersen (Senior Advisor) | Dept. of Personnel and Organisation / Recruitment Unit and Unit for Leadership and Organisational Development Dept. of Campus Management USN Stipendiary and Post Doc. Organisation (SPO) Research and Research Education Unit |  | Project finalysed. Implementation of detailed action plan in process.
6 | Initiate a project for exploring how USN may institutionalize arrangements for sabbatical leave | Organisational development project aimed at exploring how USN may clarify arrangements for sabbatical leave at institutional level | New | Pillar 1, principle 1 | 4Q_2026 | Dept. of Personnel and Organisation | Unit for Leadership and Organisational Development | Christian Brørs (Senior Advisor) | Dept. of Research, Innovation and Library |  | Initial pilot compleeted and presented for management groupe. Regulations for sabbatical leave to be finalyzed by working groupe.
7 | Further improve on-boarding for PhDs. | Pilot and further develop an annual cross faculty on-boarding day: "PhD Get started" aimed at clarifying roles and responsibilities, identifying resources and support regarding career planning, work-life balance, mobility, working conditions, sick leave and general information about rules and guidelines. | on-going | Pillar 1, principle 1 | 4Q_2025 | Dept. of Research, Innovation and Library | Research and Research Education Unit | Aina Enstad (Senior Advisor) | Dept. of Personnel and Organisation / Recruitment Unit |  | A pilot programme was developed and successfully implemented. Further development is ongoing, with consideration being given to integrating all or parts of the content within individual doctoral programmes instead of delivering it through a common institutional format. Work is also underway to standardise and quality-assure onboarding and initial follow-up meetings for PhD candidates, with the objective of ensuring that all candidates receive timely, comprehensive and consistent information upon enrolment.
PILLAR 4: Research Careers and Talent Development
8 | Organisational development project aimed at strengthening career services for PhDs and Post doctors. | The project aims to establish a holistic and systematic career development framework for PhD candidates and postdoctoral researchers. Building on existing support structures and good practices, it will identify areas for improvement and provide a foundation for future career guidance services, policies, mentoring schemes, and role definitions. The objective is to strengthen and coordinate career support across the institution, in alignment with national requirements and the Norwegian Framework for Career Development for Early-Stage Researchers, supporting career paths both within and beyond academia. | on-going | Pillar 4, principle 1-4 Pillar 3, principle 1-2 Pillar 1, principle 7 | 2Q_2026 | Dept. of Research, Innovation and Library | Research and Research Education Unit | Aina Enstad (Senior Advisor) | Dept. of Personnel and Organisation / Unit for Leadership and Organisational Development Faculties/departments PhD Fellows and Post doctors |  | The organisational development project has been completed. Work is ongoing with faculties and doctoral programmes to align and implement the resulting recommendations.
9 | Develop pilot for career planning course for PhD Fellows and Post doctors. | Half day seminar for early stage researchers (R1-R2) Examples of content; - Individual career plan - Required skills and competencies - Academic assessment - Career promoting activities - Mobility and networking - Career paths outside academia - Transversal/transferable knowledge and skills - CV writing and interview preparation - Innovation and start-ups | New | Pillar 4, principle 2 Pillar 4, principle 1, 3, 4 Pillar 3, principle 1-2 Pillar 1, principle 7 | 2Q_2027 | Dept. of Research, Innovation and Library | Research and Research Education Unit | Aina Enstad (Senior Advisor) | Dept. of Personnel and Organisation / Recruitment Unit and Unit for Leadership and Organisational Development Academic environment at USN related to MSc in Career Counselling Public Career Counselling Service |  | Currently in progress, but rescheduled to allow for consultation and alignment with the faculties and programmes regarding their preferences and requirements.
10 | Further implement new templates for individual career development plans. | As part of the implementation of newly developed templates for individual career planning; develop a "train the trainer" - course about career planning for Heads of department, PhD supervisors, Research Group Leaders and other contributors involved in the career planning for PhDs and Post Docs. Ensure knowledge about academic assessment system (USN-CAM), roles & responsibilities, templates for "Career conversation" and "Career Development Plan", relevant internal and external recourses and support services. | New | Pillar 4, principle 2 Pillar 4, principle 1, 3, 4 Pillar 3, principle 1-2 Pillar 1, principle 7 | 2Q_2027 | Dept. of Personnel and Organisation | Unit for Leadership and Organisational Development | Christian Brørs (Senior Advisor) | Academic environment at USN related to MSc in Career Counselling Dept. of Research, Innovation and Library Research and Research Education Unit |  | Currently in progress, but rescheduled to allow for consultation and alignment with the faculties and programmes regarding their preferences and requirements.
11 | Develop and implement career days for PhDs. | Initiated as a part of USNs participation in the European Digital UniverCity - alliance (EDUC) A 3-day event with workshops, seminars, lectures, career activities/information, meetings with rep. from public and private sector. To lay the foundations for annual USN career days for PhDs and Post Docs, arranged in coordination with SPO annual meeting. | on-going | Pillar 4, principle 2 Pillar 4, principle 1, 3, 4 Pillar 3, principle 1-2 Pillar 1, principle 7 | 2Q_2027 | Dept. of Research, Innovation and Library | Research and Research Education Unit | Aina Enstad (Senior Advisor) / Rebeca | Dept. of Personnel and Organisation / Recruitment Faculties/Departments USN Stipendiary and Post Doc Organisation (SPO) |  | Currently in progress, but rescheduled to allow for consultation and alignment with the faculties and programmes regarding their preferences and requirements.
12 | Further develop research leadership programme. | This leadership programme is designed for research group and research centre leaders, focusing on strategic research leadership and the development of leadership competencies within national and international research and innovation contexts. First launched in 2023, the programme will be delivered for a second time in 2025. Future development may include an English-language hybrid format, participation from EDUC and VINST partner institutions, and the recognition of learning outcomes through micro-credentials. | on-going | Pillar 4, principle 3 | 4Q_2027 | Dept. of Personnel and Organisation | Unit for Leadership and Organisational Development | Christian Brørs (Senior Advisor) | Dept. of Research, Innovation and Library |  | The programme is continuously developed to ensure high quality and relevance. Collaboration with partners in the VINST Alliance has been established, with a joint delivery of the programme planned for autumn 2027.
13 | Research project management course to be offered regularly | This course supplements the above mentioned leadership programme and addresses managers of research projects. After positive response when first offered in 2023 it is now under consideration how to make this a regular event. To be aligned with RM Comp. | on-going | Pillar 4, principle 3 Pillar 3, principle 3-4 | 2Q_2026 | Dept. of Research, Innovation and Library | Research and Research Education Unit | Ryan T. Europa (Senior Advisor) |  |  | In place and is now conducted twice annually.
14 | Initiate a project for exploring how USN may establish a development program for early stage research talents | Initiate project for building on the experience with similar programmes at partner universities in order to explore how USN may develop a programme providing scientific staff (R2-R3) with increased opportunities to develop as researchers and innovators, aiming at: - more applications and approved projects - networks and new international partners - cross-collaboration (internal) - professor promotion | New | Pillar 4, principle 3 Pillar 1, principle 1 and 3 | 4Q_2027 | Dept. of Personnel and Organisation | Unit for Leadership and Organisational Development | Christian Brørs (Senior Advisor) | Dept. of Research, Innovation and Library |  | Pilot 1 compleeted, pilot 2 ongoing 2026 - 2027, assessment and prossible proposal for permanemt institutional program planned autumn 2027